## Sheet1
Timline / Heat Map | Line Ref | Risk Level | Title | Symbol | Heat Map Dates | Date From | Date To
Timeline | Enterprise | High - Production Planning | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-12-01
Timeline | Enterprise | High - Production Planning | Go Live | Milestone | N/A | 2025-12-01 | 2025-12-01
Timeline | Enterprise | High - Production Planning | Adoption & Reinforcement | Grey Bar | N/A | 2025-12-01 | 2026-03-01
Timeline | P1 | Medium - Finance | Delivery | Blue Bar | N/A | 2025-11-11 | 2026-01-11
Timeline | P1 | Medium - Finance | Go Live | Milestone | N/A | 2026-01-11 | 2026-01-11
Timeline | P1 | Medium - Finance | Adoption & Reinforcement | Grey Bar | N/A | 2026-01-11 | 2026-05-12
Timeline | P2 | Low - All | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-12-01
Timeline | P2 | Low - All | Go Live | Milestone | N/A | 2025-12-01 | 2025-12-01
Timeline | P2 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2025-12-01 | 2026-03-01
Timeline | P3 | Low - All | Delivery | Blue Bar | N/A | 2025-11-11 | 2026-01-11
Timeline | P3 | Low - All | Go Live | Milestone | N/A | 2026-01-11 | 2026-01-11
Timeline | P3 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2026-01-11 | 2026-05-12
Timeline | P4 | Low - All | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-07-01
Timeline | P4 | Low - All | Go Live | Milestone | N/A | 2025-07-01 | 2025-07-01
Timeline | P4 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2025-07-01 | 2025-10-11
Heat Map | BAU Leave | N/A | N/A | Red | 2025-09-01
Heat Map | BAU Leave | N/A | N/A | Black | 2025-12-01
Heat Map | BAU Leave | N/A | N/A | Red | 2026-03-01
Heat Map | Engagement | N/A | N/A | Black | 2025-06-01
Heat Map | Engagement | N/A | N/A | Red | 2025-12-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-06-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-07-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-08-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-09-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-10-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-11-01
Heat Map | Project Engagement | N/A | N/A | Black | 2025-12-01
Heat Map | Project Engagement | N/A | N/A | Black | 2026-01-01
Heat Map | Project Engagement | N/A | N/A | Black | 2026-02-01
Timeline | Enterprise | High - Production Planning | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-12-01
Timeline | Enterprise | High - Production Planning | Go Live | Milestone | N/A | 2025-12-01 | 2025-12-01
Timeline | Enterprise | High - Production Planning | Adoption & Reinforcement | Grey Bar | N/A | 2025-12-01 | 2026-03-01
Timeline | P1 | Medium - Finance | Delivery | Blue Bar | N/A | 2025-11-11 | 2026-01-11
Timeline | P1 | Medium - Finance | Go Live | Milestone | N/A | 2026-01-11 | 2026-01-11
Timeline | P1 | Medium - Finance | Adoption & Reinforcement | Grey Bar | N/A | 2026-01-11 | 2026-05-12
Timeline | P2 | Low - All | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-12-01
Timeline | P2 | Low - All | Go Live | Milestone | N/A | 2025-12-01 | 2025-12-01
Timeline | P2 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2025-12-01 | 2026-03-01
Timeline | P3 | Low - All | Delivery | Blue Bar | N/A | 2025-11-11 | 2026-01-11
Timeline | P3 | Low - All | Go Live | Milestone | N/A | 2026-01-11 | 2026-01-11
Timeline | P3 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2026-01-11 | 2026-05-12
Timeline | P4 | Low - All | Delivery | Blue Bar | N/A | 2025-06-01 | 2025-07-01
Timeline | P4 | Low - All | Go Live | Milestone | N/A | 2025-07-01 | 2025-07-01
Timeline | P4 | Low - All | Adoption & Reinforcement | Grey Bar | N/A | 2025-07-01 | 2025-10-11

## Sheet2
Blue Bar
Grey Bar
White Bar
Red Bar
Milestone
Black Spot
Red Spot